# PUBLISHABLE EXECUTIVE SUMMARY

## 1. Summary description of the project objectives

The aim of the CENTRAL LOCO project is to promote dissemination and exploitation of results of RTD projects of the 5th and 6th Framework Programmes among the enterprises and research units operating in logistics and transport sector. These organisations are insufficiently experienced both in knowledge transfer from leading institutions in the EU and in coordinating the cooperation between the research and industry. This is particularly true regarding the issue of safe, secure and efficient intermodal transport where such transfer and co-operation are urgently needed.

The main objective of the CENTRAL LOCO project would be achieved by creating a set of networking and knowledge transfer activities, including one conference, two practical workshops, web pages, and newsletters targeted at companies, research and business support organizations. The project’s area of influence are four Central-European New Member States known as the Vysehrad Four: Czech Republic, Hungary, Poland and Slovakia.

## 2. List of Contractors

| Partic. No. | Participant name | Participant short name | Country |
| --- | --- | --- | --- |
| 1 | Institute of Logistics and Warehousing | ILiM | Poland |
| 2 | Transport Research Centre | CDV | Czech Republic |
| 3 | Institute for Transport Sciences Ltd. | KTI | Hungary |
| 4 | Research Institute for Transport | VUD | Slovakia |

## 3. Co-ordinator contact details

Institute of Logistics and Warehousing, ul. E. Estkowskiego 6, 61-755 Poznan, Poland

Tel.No.: +48 61 850 49 35, Fax No.: +48 61 852 63 76

E-mail: maciej.tumasz@ilim.poznan.pl

## 4. Project website:

www.centralloco.net

## 5. Project logo:

## 6. Work performed and results achieved

The main activities performed during the first reporting period f the CENTRAL LOCO project included:

- Organisation of the kick-off meeting in June 2005, in Rajecke Teplice (Slovakia)

During the first meeting of the consortium, partners had a chance to present their organisations and discuss important issues related to the project execution. Apart from discussing the content of the WP's, the presentation of the Commission's requirements and procedures was delivered by the coordinator on behalf of the Project Officer.

- Launching the project website in October 2005: www.centralloco.net

The website presents the project, its activities, planned events and reports from the organised conference and workshop. It also enables interested users to subscribe for a project newsletters and to get access to the project documents, such as presentations, reports, photos, lists of participants, etc.

- Organisation of the first project workshop in November 2005 in Prague (Czech Republic)

During the first 2-day workshop titled “New telematic solutions in logistics” ten interesting presentations were presented and discussed. The expected result envisaged in the project proposal (at least 20% of all participants should be companies) was reached as around 40% of organisations present during the workshop were enterprises.

- Identification of EU RTD projects in the field of logistics and intermodal transport,

The database containing over 120 different projects in the field of logistics has been constantly updated. It is available in English and in Polish on the web site http://www.polloco.pl/projects/index.php.

- Organisation of the project conference within the Polish Logistics Congress LOGISTICS 2006. Three thematic sessions were prepared by the CENTRAL LOCO consortium. During the conference best practice solutions in different fields of logistics (i.e.: ECR, SCM, Reverse logistics, outsourcing, CRM, CPF, Reengineering, intermodal transport, e-logistics, etc.) were presented and discussed. It was planned to achieve 200 participants and the result exceeded three times as there were more than 600 participants.

- Creation of opportunities for new projects among members of research and business communities and invitation of large numbers of companies to participate in Framework Programmes during organised events

- Provision of the access to conference and workshop materials both in English and national languages.

During the next year of CENTRAL LOCO duration the second project workshop will be organised (Jan-Feb. 2007, Budapest). The newsletters will be prepared and emailed to the receivers from different European countries. The coordinator and the partners will continue their efforts to perform and fulfil the project objectives, which lead to create a European platform of the logistics and transport knowledge.